PROGRESS REPORT ON STRATEGIC PLANS

SPD Education Committee, October 2024

| Strategy 1: Ensure Adventist Identity remains a key part of Adventist Education |  |  |  |  |
| --- | --- | --- | --- | --- |
| Strategy | Progress | Outcome Metrics | Follow up | Impact Assessment & Future Outlook |
| 1. Adventist Ethos Workshops | - Training completed in TPUM & PNGUM | - Train the trainer a success - Programs very well attended | Follow-up to embed training into school policy and practice. | https://record.adventistchurch.com/2023/04/24/200-educators-attend-workshop-on-adventist-identity-and-ethos/?fbclid=IwAR0xfUF5msvGFFs3aikv_RhbOzSO5f2v2fu5C8b2-KBVk89gZZDgo7FQCdg |
| 2. Faith Development and School Climate Research | - Student data collection - School focus groups | - Data to be analysed - Project balance: $247,000 - Tamar Aiono, PhD candidate, joined the research team | Complete the research phase and create an instrument to assess and report on faith development & school climate indicators. | - Faith Development-School Climate Dashboard* - Substitution of this research for components of Insight SRC school climate data collection and analysis* |
| 3. Adventist Ethos Project | Production of short ethos videos | Project balance: $106,000 | Videos to be completed by Q2, 2024 |  |
| 4. Pacific Bible Curriculum | Preparing for re-printing | Project balance: $5100 |  | Ascertain the need for re-printing of hardcopy volumes. |
|  |  |  |  | - Book of Faith & Science conference presentations Q3-4, 2023 - Abide Bibles – AUC Project; Q4 2023 - Abide Presentations – Adelaide teachers October, 2023 |

| Strategy 2: Develop and Grow our education leadership team. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Strategy | Progress | Outcome Metrics | Follow up | Impact Assessment & Future Outlook |
| 1. Increasing pool of potential leaders | - Advanced Study Committee: - Collating of all sponsorships | - Wide range of sponsorships - Informs Succession Plan | Succession planning has identified key staff needing doctoral studies etc. | - BMTE committee development of Pacific-wide delivery of MMin* to be circulated by February 2024. - Identify future specialisations needed by church entities – for 2024 advisories* |
| 2. Succession Planning | - Construction of a single Succession Plan document | - Identification of doctoral candidates. - Identification of PD | - Refer doctoral candidates to ASC. - Advisories to plan PD programs in PARL, system leadership. - System-wide appraisal program is not in place. | - Advisories to discuss emerging leaders’ programs in Pacific* - Seek project funding to develop a Pacific-wide appraisal and leadership development program* |
| 3. Support emerging leader programs | - VM Education Conference - NZPUC Leadership Hui | - Address form Director of Education Services for the Vanuatu Ministry of Education presented data and affirmed success of high schools |  | - Prospect of moving to a Pacific version of AUC’s Quality Adventist Schools Framework |
| 4. Include PD into SPD Advisories /EdCom | PD presentations as part of the BOE agenda | - Sabbath Gift promotion - AI as a learning support tool presentation |  | Encounter presentation |

| Strategy 3: Educational Improvement. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Strategy | Progress | Outcome Metrics | Follow up | Impact Assessment & Future Outlook |
| 1. Review AAA processes | Conduct AAA reviews across the SPD Higher Ed institutions | AAA Completed for: - Fulton – 4 yrs - Sonoma – 4 yrs + midterm - PAU – 4 yrs - Avondale - 2025 | Review institutional boards to ensure AAA recommendations are regularly reviewed and addressed. | Collate a AAA response register at SPD for inclusion at SPD Education Committee* ** For discussion at SPD Ed Committee March 2024. |
| 2. Implement school improvement tools |  | QAS Cyclic Review Visit to Betikama, SIM, DEC 2023 | Create and implement school and system appraisal resources. | - Pacific QAS modifications to include revision of rating criteria and training of school and system leaders: Q1-2, 2024 Participant on AAA teams in India for: - METAS – Surat / Nuzvid / Ranchi - North East Adventist University |
| Strategy 4: System Support. |  |  |  |  |
| 1. Review MOUs |  |  |  | Establish MOU register at SPD* |
| 2. Pacific Partnerships | PTC SMS Project | - Staff from Montemorelos at Fulton then the PNG institutions Grace Paulson now at PAU | Suggestion from SPD to utilise Luke Pannekoek to improve PTC SMS Project governance. | Exploring capacity building across research training, research projects, curriculum devt, benchmarking, governance training for the tertiary entities. |
|  |  |  | - Assisting Avondale with TEQSA Submission - Participated in Hills Adventist College service trip to SIM. - Collate higher education sector grad destination survey data. - Collate data to review staff turnover patterns esp. mid-career teachers. - Collate higher education sector graduate numbers. |  |

Final Comments:

At the last SPD Education Committee, the risk created by mid-career teachers leaving the professional was highlighted.  With that in mind, to assist with focussing any potential resolutions, please review the following:

Teachers-Perceptions-of-their-Work-2022.pdf (monash.edu)

In preparation for discussion of future strategic goals for the SPD Education Department please also familiarize yourself with these documents:

Spotlight_Vol_15_Issue_1.pdf (pngnri.org)

Remote PNG school students abandoned as village violence stops teachers showing up, headmaster says - ABC News